## Index (hidden)
| Planned | Actual
Leads Generated- Region Wise- by BD | #REF! | #REF!
Leads Generated- Region Wise- by Others | #REF! | #REF!
Leads matured to NIT- by BD | #REF! | #REF!
Leads matured to NIT- by Others | #REF! | #REF!
Bids Submitted from leads matured- by BD | 0 | #REF!
Bids Submitted from leads matured- by Others | 0 | #REF!
| BD | Others
Leads | #REF! | #REF!
NIT | #REF! | #REF!
Proposals | #REF! | #REF!
Win-Loss %
| Actual | 40%
| Target | 50%

## Draft- Dashboad (hidden)
DASHBOARD
All values in INR Cr.
LEAD IDENTIFICATION & CLIENTELE BASE
|  |  |  | TOTAL LEADS | INR (Crs.)
#REF!
HIGH
#REF!
MEDIUM
#REF!
LOW
#REF!
COLLECTION OVERVIEW
| HP, Chandigarh, Haryana, Punjab | Chandrawal WTP Command Area (Package 2: West Zone)
PROPOSAL SUBMISSION
[6 empty] | Proposals Due in Next 7 days | No Of Project | Estimated Cost
[6 empty] | Chandigarh | 1 | 55.577
[6 empty] | Project A | 1 | 55.577
|  |  | Southern Region | L&T |  | Karnataka | 1 | 1210
[6 empty] | Project B | 1 | 1210
[6 empty] | Rajasthan | 3 | 646.666
[6 empty] | Project C | 1 | 167
[6 empty] | Project D | 1 | 270
[6 empty] | Project E | 1 | 209.666
[6 empty] | Grand Total | 5 | 1912.243
[6 empty] | Proposals Due in Next 15 days | No Of Project | Estimated Cost
ORDER BOOK STATUS
FY: Previous
INR 1700 Crs.
FY: Current
INR 1700
INR 0
TARGET
ACTUAL
WIN-LOSS %
TARGET PROPOSAL SUBMISSIONS
INR 800 Crs.
WORKS COMPLETED
INR 260 Crs.
BILLS RAISED
INR 250 Crs.
PAYMENTS RECEIVED
INR 200 Crs.
LEADS STATUS
REGION
PROJECT
AGEING (In Days)
INR 20 Crs.
< 30
>30 & <45
INR 10 Crs.
> 45
INR 5 Crs.
COMPETITOR ANALYSIS
PROPOSAL STATUS
STATE
COMPETITOR
No. of Projects Executed
Value of Projects Executed
No. of Ongoing Projects
Value of Ongoing Projects
LEADS SELECTION
CLIENTELE
INR 250 Crs.
10
INR 250 Crs.
10

## Daft- Dashboard 2 (hidden)
DASHBOARD
All values in INR Cr.
1700
LEAD IDENTIFICATION & CLIENTELE BASE
COLLECTION OVERVIEW
|  |  |  | #REF! |  | #REF! |  | #REF! |  | #REF!
PROPOSAL SUBMISSION
[9 empty] | Proposals Due in Next 7 days |  | No Of Project | Estimated Cost
[9 empty] | Chandigarh |  | 1 | 55.577
[9 empty] | Project A |  | 1 | 55.577
[9 empty] | Karnataka |  | 1 | 1210
[9 empty] | Project B |  | 1 | 1210
[9 empty] | Rajasthan |  | 3 | 646.666
[9 empty] | Project C |  | 1 | 167
|  | No. of Projects Executed | Value of Projects Executed |  | No. of Ongoing Projects |  | Value of Ongoing Projects |  | Project D |  | 1 | 270
[9 empty] | Project E |  | 1 | 209.666
[9 empty] | Grand Total |  | 5 | 1912.243
|  | #REF! | #REF! |  | #REF! |  | #REF!
[9 empty] | Proposals Due in Next 15 days |  | No Of Project | Estimated Cost
ORDER BOOK STATUS
FY: Previous
FY: Current
TARGET
ACTUAL
WIN-LOSS %
TARGET PROPOSAL SUBMISSIONS
INR 800 Crs.
Project Value
BILLS RAISED
PAYMENTS RECEIVED
LEADS STATUS
COMPETITOR ANALYSIS
PROPOSAL STATUS
LEADS SELECTION
CLIENTELE
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
AGEING (In Days)

## Dashboard (3)
FINANCIALS
| Previous Year |  |  | Current Year
|  |  |  | TARGET |  |  | ACTUAL
| 1700 |  |  | 2000 |  |  | 500
| Number NIT released and not identified |  |  |  | Number of wins with High Opporunity Score
| 3 |  |  |  | 2
| TOTAL SUBMITTED |  | CERTIFIED BILLS |  |  | RETENTION AMOUNT |  |  | PAYMRNT RECEIVED |  | AVERAGE AGEING |  |  | TOTAL LIABILITY |  |  | JINDAL SAW LIABILITY |  |  | AVERAGE AGEING
[11 empty] | < 60 Days | > 60 Days | [7 empty] | < 60 Days |  | > 60 Days
| 107.55 |  | 53.77 |  |  | 2.4 |  |  | 48.97 |  | 53.78 | 0 |  | 67.52 |  |  | 65.78 |  |  | 27.02 |  | 40.5
STAKEHOLDER
[16 empty] | AVERAGE SATISFACTION INDEX FOR THE YEAR (ASI) | [6 empty] | 21%
PROCESS
Average Ageing (In Days)
25
[13 empty] | Control Points |  | Control Points Adhered |  |  | Templates Provided |  |  | Templates Adhered
[13 empty] | 163 |  | 95 |  |  | 85 |  |  | 55
CAPABILITY
|  | Total Roles Identified | [5 empty] | 22 |  | Hirings Planned | [8 empty] | Average TAT (In Days)
85
51.0465
|  | Total Successors Identified | [5 empty] | 16
Hirings Completed
[10 empty] | 81 | [8 empty] | Achievement Rate
|  | Total Skill Gap Assessed | [5 empty] | 11
[10 empty] | Unplanned Hirings | [8 empty] | 27.91%
17
ORDER BOOK STATUS
DASHBOARD- CEO KPI's
PROFITABILITY AT PORTFOLIO & PROJECT LEVEL
PROJECT BUDGET COMPLIANCE
PROFIT & LOSS STATEMENT (In Crores)
CLAIMS MANAGEMENT
CASHFLOW (In Crores)
EMPLOYEE ATTRITION
SCHEDULE PERFORMANCE
QHSE ADHERENCE
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
CONTROL ASSESSMENT
EMPLOYEE HIRING TAT
BONUS ACHIEVEMENT STATUS
JWIL SUCCESSION PLAN
Q
M
Q
M
M
F
M
M
M
F
M
Q
M
Q
M
A
H
F
ANNUALY
HALF YEARLY
QUARTERLY
MONTHLY
FORTNIGHTLY
ANNUAL HIRING PLAN
M
RECEIVABLES YTD (in Crs.)
LIABILITIES YTD (in Crs.)
MONTH
PORTFOLIO
PROJECT
LITIGATION STATUS
EMPLOYEE ENGAGEMENT
A
Q
COMPLIANCE STATUS
MONTH
PORTFOLIO
PROJECT
MONTH
PORTFOLIO
PROJECT
MONTH
PORTFOLIO
PROJECT
MONTH
PORTFOLIO
PROJECT
MONTH
PORTFOLIO
PROJECT
MONTH
PORTFOLIO
PROJECT
MONTH
PORTFOLIO
PROJECT
MONTH
PORTFOLIO
PROJECT
MONTH
PORTFOLIO
PROJECT

## Sheet2
Project Name | Sale | Direct | Gross Profit | Employee | Admin | HO Employee | HO Admin | Total | EBITA
|  | Cost |  | Cost | Expense | Allocation | Allocation | Indirect Cost
Parwaan
Adityapur
Byarma
Total - New Project
Guwahati C1
Guwahati C3
Total - Guwahati
Munger
Jamalpur
Mau
DJB -Kalyanpuri
NTPC
Sidhi
Silao
Sehore
Agra
Manpur
Rajauli
Tikamgarh
Morena
Nepal Package 1
Total - Old Project
Bodhgaya
Nayaraipur
Dehradun
Tamnar
Total - Other Project
Bodhgaya-O & M
Morena-O & M
Mau WSS-O & M
Sehore-O & M
Total - O & M
Corporate
Total
|  |  | M1 | M2 | M3
|  | Revenue | 100 | 80 | 90 | 270
|  | DC | 70 | 60 | 75 | 205
|  | IDC | 20 | 15 | 12 | 47
|  | EBITA | 10 | 5 | 3 | 18 | 0.066667
|  |  | Revenue | DC | IDC | EBITA
|  | M1 | 100 | 70 | 20 | 10
|  | M2 | 80 | 60 | 15 | 5
|  | M3 | 90 | 75 | 12 | 3
|  | Revenue | 270
|  | DC | 205
|  | IDC | 47
|  | EBITA | 18
|  | Project Name | Contractual Period | Forecasted Completion | Potential Bonus (In Crores) | Bonus Achieved (In Crores)

## Dashboard (2) (hidden)
| FY: Previous | FY: Current
|  | TARGET |  | ACTUAL
| 1700 | 2000 |  | 500
Number of wins with High Opporunity Score
2
Number NIT released and not identified
3
[7 empty] | AVERAGE SATISFACTION INDEX (ASI) |  |  | 76%
| Ask CEO Call | [5 empty] | NPS |  |  | xx
6
One on One Session
80
| Business Improvement suggestions shared by employees |  |  |  | 120
[8 empty] | Total number of compliance |  |  |  | 0 | Average TAT (In Days)
[8 empty] | Compliance due in this month |  |  |  | 0 | 51.0465
[8 empty] | PF Compliance Status |  |  |  | Complete | Achievement Rate
[8 empty] | ESI Compliance Status |  |  |  | Complete | 27.91%
INTERNAL AUDIT COMPLIANCE REPORT
[6 empty] | Control Points |  |  | Control Points Adhered |  | Templates Provided |  |  | Templates Adhered
[6 empty] | 163 |  |  | 95 |  | 85 |  |  | 55
ORDER BOOK STATUS
DASHBOARD- CEO KPI's
PROFITABILITY AT PORTFOLIO & PROJECT LEVEL
PROJECT BUDGET COMPLIANCE
EBITA
CLAIMS MANAGEMENT
Billable Claim by JWIL
Claim paid to sub-contractors
CASHFLOW (In Crores)
ORDER BOOK FROM TECH & O&M
(In Crores)
LITIGATION STATUS
EMPLOYEE ENGAGEMENT
EMPLOYEE ATTRITION
EMPLOYEE CONNECT & INVOLVEMENT
PARTNER OF CHOICE - CLIENT
FEEDBACK FROM VENDORS
SCHEDULE PERFORMANCE
QUALITY ADHERENCE
INSPECTION REPORT RESOLVED OFF AGAINST TOTAL RAISED
NUMBER OF NCR RAISED BY CLIENT
SAFETY ADHERENCE
SAFE WORKING HOURS
NUMBER OF NCR RAISED BY CLIENT
TRAINING STATUS
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
CONTROL ASSESSMENT
COMPLIANCE STATUS
EMPLOYEE HIRING TAT

## Dashboard (hidden)
FINANCIALS
| FY: Previous |  |  | FY: Current
|  |  |  | TARGET |  |  | ACTUAL
| 1700 |  |  | 2000 |  |  | 500
Number of wins with High Opporunity Score
2
Number NIT released and not identified
3
STAKEHOLDER
[11 empty] | AVERAGE SATISFACTION INDEX (ASI) |  |  | 21%
| Ask CEO Call |  |  |  | One on One Sessions by HoD | [5 empty] | NET PROMOTER SCORE (NPS)
| Planned |  | Actual |  | Planned |  |  | Actual
| 16 |  | 8 |  | 64 |  |  | 48
20%
| Business Improvement suggestions shared by employees | [7 empty] | 120
PROCESS
[16 empty] | Average Ageing (In Days) |  |  | 25
[13 empty] | Control Points |  | Control Points Adhered |  | Templates Provided | Templates Adhered
[13 empty] | 163 |  | 95 |  | 85 | 55
CAPABILITY
[10 empty] | Mandatory Taining Hours |  | 80
[10 empty] | Average Training Hours Completed |  | 46
|  | Total Roles Identified | [5 empty] | 22 | [8 empty] | Average TAT (In Days)
51.0465
|  | Total Successors Identified | [5 empty] | 16
Achievement Rate
|  | Total Skill Gap Assessed | [5 empty] | 11
27.91%
ORDER BOOK STATUS
DASHBOARD- CEO KPI's
PROFITABILITY AT PORTFOLIO & PROJECT LEVEL
PROJECT BUDGET COMPLIANCE
EBITA
CLAIMS MANAGEMENT
Billable Claim by JWIL
Claim paid to sub-contractors
CASHFLOW (In Crores)
ORDER BOOK FROM TECH & O&M
(In Crores)
LITIGATION STATUS
EMPLOYEE ENGAGEMENT
EMPLOYEE ATTRITION
EMPLOYEE CONNECT & INVOLVEMENT
PARTNER OF CHOICE - CLIENT
FEEDBACK FROM VENDORS
SCHEDULE PERFORMANCE
SAFETY ADHERENCE
SAFE HOURS
NUMBER OF NCR RAISED BY CLIENT
QUALITY ADHERENCE
DIGITAL CAPABILITY
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
CONTROL ASSESSMENT
EMPLOYEE HIRING TAT
BONUS ACHIEVEMENT STATUS
INTERNAL AUDIT OBSERVATION
COMPLIANCE STATUS
TRAINING STATUS
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
JWIL SUCCESSION PLAN
REVENUE FROM INHOUSE OPERATIONS
Q
M
A
Q
Q
M
M
F
M
M
Q
Q
A
A
A
F
F
F
M
M
Q
Q
Q
M
H
H
A
Q
M
A
H
F
ANNUALY
HALF YEARLY
QUARTERLY
MONTHLY
FORTNIGHTLY

## Lead Report
[17 empty] | Date | [5 empty] | 2020-04-10
Procedure for Lead Generation, Management & Review Document No: Datasheet of Leads for Reporting & Feedback
Business Development
Delhi + Bihar + International
Maharashtra, Rajasthan
Uttar Pradesh
Southern Region
HP, Chandigarh, Haryana, Punjab
Gujarat, Madhya Pradesh
West Bengal, Jharkhand
Datasheet of Leads for Reporting & Feedback
MONTH
[11 empty] | Prioritization of Leads | [7 empty] | Selection
[11 empty] | 10% | 20% | 20% | 15% | 15% | 20%
S.No. | Region (Use dropdown to chose particular region) | State | Name of BD Representative | Name of Client | Name Of Project | Estimated Cost (In Crs.) | Funding Agency | Department Contact details | Tentative Date of Release of NIT | Bidding by Single/JV | Project Value | Scope of Work | Project Location/ Geography | Past Experience with client | Government Support | Competition landscape on opportunity | Impact Score | Lead Category | Low | Medium | High | Process Status | Remarks
1 | Uttar Pradesh |  |  | Karnataka Urban Infrastructure Development & Finance Corporation Ltd. [KUIDFC] | Project 1 | 740 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | LOW | 740 | FALSE | 0
2 | Delhi + Bihar + International |  |  | Karnataka Urban Infrastructure Development & Finance Corporation Ltd. [KUIDFC] | Project 2 | 1210 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | LOW | 1210 | FALSE | 0
3 | HP, Chandigarh, Haryana, Punjab |  |  | Engineer-in-Chief - Water Resources Department | Project 3 | 306.8062 |  |  |  |  | 2 | 1 | 3 | 2 | 3 | 1 | 1.95 | MEDIUM | 0 | 306.8062 | 0
4 | Southern Region |  |  | DJB | Project 4 | 200 |  |  |  |  | 2 | 3 | 1 | 1 | 1 | 2 | 1.7 | MEDIUM | 0 | 200 | 0
5 | Maharashtra, Rajasthan |  |  | DJB | Project 5 | 520 |  |  |  |  | 3 | 2 | 3 | 3 | 3 | 2 | 2.6 | HIGH | 0 | 0 | 520
6 | Gujarat, Madhya Pradesh |  |  | BWSSB | Project 6 | 720 |  |  |  |  | 3 | 2 | 3 | 3 | 3 | 2 | 2.6 | HIGH | 0 | 0 | 720
7 | West Bengal, Jharkhand |  |  | BWSSB | Project 7 | 500 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | LOW | 500 | FALSE | 0
8 | Uttar Pradesh |  |  | MP Industrial Development Corporation Limited | Project 8 | 42.6 |  |  |  |  | 2 | 1 | 3 | 2 | 3 | 1 | 1.95 | MEDIUM | 0 | 42.6 | 0
9 | Delhi + Bihar + International |  |  | PHED-Chief Engineer(HQ),Jaipur | Project 9 | 209.666 |  |  |  |  | 2 | 3 | 1 | 1 | 1 | 2 | 1.7 | MEDIUM | 0 | 209.666 | 0
10 | HP, Chandigarh, Haryana, Punjab |  |  | Karnataka Urban Water Supply and Drainage Board | Project 10 | 132.8197 |  |  |  |  | 3 | 2 | 3 | 3 | 3 | 2 | 2.6 | HIGH | 0 | 0 | 132.8197
11 | Southern Region |  |  | PHED-Chief Engineer(HQ),Jaipur | Project 11 | 378.48 |  |  |  |  | 1 | 2 | 1 | 1 | 1 | 1 | 1.2 | MEDIUM | 0 | 378.48 | 0
12 | Maharashtra, Rajasthan |  |  | BUIDCO | Project 12 | 198.4669 |  |  |  |  | 2 | 1 | 3 | 2 | 3 | 1 | 1.95 | MEDIUM | 0 | 198.4669 | 0
13 | Gujarat, Madhya Pradesh |  |  | Engineers India Limited,MoPNG | Project 13 | 350 |  |  |  |  | 2 | 3 | 1 | 1 | 1 | 2 | 1.7 | MEDIUM | 0 | 350 | 0
14 | West Bengal, Jharkhand |  |  | Engineers India Limited,MoPNG | Project 14 | 425 |  |  |  |  | 3 | 2 | 3 | 3 | 3 | 2 | 2.6 | HIGH | 0 | 0 | 425
| GRAND TOTAL |  |  |  |  | 5933.8388 | [12 empty] | 2450 | 1686.0191 | 1797.8197

## NIT's Report
[16 empty] | Date | 2020-04-10 |  | Date | 2020-04-10
Procedure for Lead Generation, Management & Review Document No: Datasheet of NIT's for Reporting & Feedback
Business Development
| Delhi + Bihar + International | HIGH | Result Awaited
| Maharashtra, Rajasthan | MEDIUM | Bids Under Consideration
| Uttar Pradesh | LOW | Bids Under Preparation
| Southern Region | UNIDENTIFIED | Bid Won
| HP, Chandigarh, Haryana, Punjab |  | Bid Lost
| Gujarat, Madhya Pradesh |  | Bids Submitted
West Bengal, Jharkhand
Review Date
Datasheet of NIT's for Reporting & Feedback | [21 empty] | 2020-04-10
MONTH | [21 empty] | 2020-04-17 | 2020-04-24 | 2020-05-01
[19 empty] | 7 Days Later | 15 Days Later
Sr. No | Types of Project | Lead Category (Lead Report to be referred) | Region (Use dropdown to chose particular region) | State | Name of Project | Name of Client | NIT Reference No | Project Brief | Duration of Project | Approx Cost (In Crores) | EMD (Lakh) | Pre Bid Meeting Date | Date of Submission | Contact Person | Consultants | Major Competitors | Status (Select from the dropdown menu) | Status & Action Plan | Remarks from BD Head | Remarks from CEO | Remarks | Proposals Due in next 7 Days | Proposals Due from 8th to 15 Days | Proposals Due post 15 Days
1 |  | MEDIUM | Southern Region | Karnataka | Design, build, operate and maintain, and transfer water supply system in Kalburgi city of Karnataka State, India for cost effective and sustainable upscaling to continuous (24x7) pressurized water supply |  |  |  |  | 740 |  | 2019-10-02 | 2019-10-23 |  |  |  | Bid Won |  |  |  |  | 0 | 0 | 0
2 |  | UNIDENTIFIED | HP, Chandigarh, Haryana, Punjab | Karnataka | Design, build,operate and maintain, and transfer water supply system in Hubballi Dharawada city of Karnataka State, India for cost effective and sustainable upscaling to continuous (24x7) pressurized water supply |  |  |  |  | 1210 |  | 2019-10-03 | 2019-10-24 |  |  |  | Bids Under Preparation |  |  |  |  | 0 | 0 | 0
3 |  | MEDIUM | Maharashtra, Rajasthan | Madhya Pradesh | On Turn-Key Basis conveying of water for hose irrigation System from Chhitakhudri and Hiran Reservoir of District Jabalpur (M.P.) to deliver water at farmerâ€™s field up to service outlet of 1 Ha chak with a outlet duty of 0.37 lit/Sec/ha and desired flow of Orifice type of nozzle as 10 times of specified duty with minimum 1.5m exit gradient on highest point of chak field along with Providing, fixing, installation and all arrangements complete of external energy sources for Chhitakhudri project having minimum CCA 12125 ha and maximum total energy consumption limited to 3.56 MW, for Hiran project having minimum CCA 8125 ha and maximum total energy consumption limited to 0.38MW and for Baghraji canal project having minimum CCA of 2800 ha including supply from Chhitakhudri dam and maximum total energy consumption limited to 0.13MW; in total CCA of 23050 Ha out of total GCA of 34090 Ha, fully covering the entire compact and contiguous possible arable area and any irrigable area increase in CCA within/ beyond the GCA shall be permitted with written approval of Chief Engineer. The work also includes all activities starting from survey, investigations, preparation of Pvt/Govt./Forest LA caseâ€™s, preparation and submission of design, drawing, estimation and its approval from the competent authority including Procurement, Construction, Laying, Installing, Energizing etc of pumping systems, rising and gravity mains, main lines, branch lines, distribution network; with all allied inline structure, including Residential Building and tar roads up to pump house, DC and all along RM/GM including controlling and regulation of system etc. for supply of water under pressure with SCADA and automation as per detailed scope of work but not limited to it. The work also includes Management, Operation and Maintenance (MOM) of complete scheme for the period of five On Turn-Key Basis conveying of water for hose irrigation System from Chhitakhudri and Hiran Reservoir of District Jabalpur (M.P.) to deliver water at farmerâ€™s field up to service outlet of 1 Ha chak with a outlet duty of 0.37 lit/Sec/ha and desired flow of Orifice type of nozzle as 10 times of specified duty with minimum 1.5m exit gradient on highest point of chak field along with Providing, fixing, installation and all arrangements complete of external energy sources for Chhitakhudri project having minimum CCA 12125 ha and maximum total energy consumption limited to 3.56 MW, for Hiran project having minimum CCA 8125 ha and maximum total energy consumption limited to 0.38MW and for Baghraji canal project having minimum CCA of 2800 ha including supply from Chhitakhudri dam and maximum total energy consumption limited to 0.13MW; in total CCA of 23050 Ha out of total GCA of 34090 Ha, fully covering the entire compact and contiguous possible arable area and any irrigable area increase in CCA within/ beyond the GCA shall be permitted with written approval of Chief Engineer. The work also includes all activities starting from survey, investigations, preparation of Pvt/Govt./Forest LA caseâ€™s, preparation and submission of design, drawing, estimation and its approval from the competent authority including Procurement, Construction, Laying, Installing, Energizing etc of pumping systems, rising and gravity mains, main lines, branch lines, distribution network; with all allied inline structure, including Residential Building and tar roads up to pump house, DC and all along RM/GM including controlling and regulation of system etc. for supply of water under pressure with SCADA and automation as per detailed scope of work but not limited to it. The work also includes Management, Operation and Maintenance (MOM) of complete scheme for the period of five Year. |  |  |  |  | 306.8062 |  | 2019-10-04 | 2019-10-25 |  |  |  | Bids Under Preparation |  |  |  |  | 0 | 0 | 0
4 |  | LOW | Southern Region | Delhi | Improvement of Water Supply System by Construction / Rehabilitation / Replacement, Supply, Laying, Installation, Testing, Commissioning of Transmission and Distribution Pipes with Appurtenances, Pumping Stations, Underground Reservoirs, Service Connections and Consumer Meters, SCADA system, along with DMA formation and NRW Reduction in a Project Construction Period of 4-years and 3.5 -years O&M during construction period plus 5-years O&M after Construction to achieve the equitable and continuous (24 hours & 7 days/week ) water distribution in the Chandrawal WTP Command Area (Package 4: East Zone) |  |  |  |  | 200 |  | 2019-10-05 | 2019-10-26 |  |  |  | Bid Won |  |  |  |  | 0 | 0 | 0
5 |  | HIGH | West Bengal, Jharkhand | Delhi | Improvement of Water Supply System by Construction / Rehabilitation / Replacement, Supply, Laying, Installation, Testing, Commissioning of Transmission and Distribution Pipes with Appurtenances, Pumping Stations, Underground Reservoirs, Service Connections and Consumer Meters, SCADA system, along with DMA formation and NRW Reduction in a Project Construction Period of 5-years and 4.5 -years O&M during construction period plus 5-years O&M after Construction to achieve the equitable and continuous (24 hours & 7 days/week ) water distribution in the Chandrawal WTP Command Area (Package 2: West Zone) |  |  |  |  | 520 |  | 2019-10-06 | 2019-10-27 |  |  |  | Bids Under Consideration |  |  |  |  | 0 | 0 | 0
6 |  | MEDIUM | Southern Region | Karnataka | Design, engineering, construction & commissioning of pump station & reservoir at Harohalli & Tataguni with O&M for 7 years â€“ DBO Package # BWSSB/JICA/CP-04 |  |  |  |  | 720 |  | 2019-10-07 | 2019-10-28 |  |  |  | Bids Under Preparation |  |  |  |  | 0 | 0 | 0
7 |  | UNIDENTIFIED | HP, Chandigarh, Haryana, Punjab | Karnataka | Design, engineering, construction & commissioning of pump station & reservoir at T.K. Halli with O&M for 7 years â€“ DBO Package # BWSSB/JICA/CP-03 |  |  |  |  | 500 |  | 2019-10-08 | 2019-10-29 |  |  |  | Bid Won |  |  |  |  | 0 | 0 | 0
8 |  | MEDIUM | Southern Region | Madhya Pradesh | Design and Construction of Industrial ETP based on ZLD ic Collection gravity pipe network, Effluent pumping stations, Master Balancing Reservoir ESR and Recycled Water Disposal Pipe Network on EPC basis and ic O and M for 5 years at VUL |  |  |  |  | 42.6 |  | 2019-10-09 | 2019-10-30 |  |  |  | Bids Under Preparation |  |  |  |  | 0 | 0 | 0
9 |  | UNIDENTIFIED | Southern Region | Rajasthan | Work of Bisalpur-Jaipur Water Supply Project Stage-II ( Phase-I) with one year defect liability, â€ i.e. Design (Selected part) & Build |  |  |  |  | 209.666 |  | 2019-10-10 | 2019-10-31 |  |  |  | Bids Under Consideration |  |  |  |  | 0 | 0 | 0
10 |  | MEDIUM | Southern Region | Karnataka | Augmentation of water supply scheme to Badami, Kerur towns and 18 enroute villages from Almatti reservoir as source (Package-I) |  |  |  |  | 132.8197 |  | 2019-10-11 | 2019-11-01 |  |  |  | Bids Under Consideration |  |  |  |  | 0 | 0 | 0
11 |  | LOW | Delhi + Bihar + International | Rajasthan | Work of Bisalpur- Prithviraj Nagar Water Supply Project Phase-I, Stage-I |  |  |  |  | 378.48 |  | 2019-10-12 | 2019-11-02 |  |  |  | Bid Won |  |  |  |  | 0 | 0 | 0
12 |  | HIGH | Southern Region | Bihar | Design and Construction of drinking water supply scheme, of Munger Nagar Nigam under AMRUT and state plan Scheme (Phase II) with six months of Trial run and thereafter operation and maintenance of system for next five years. |  |  |  |  | 198.4669 |  | 2019-10-13 | 2019-11-03 |  |  |  | Bids Under Preparation |  |  |  |  | 0 | 0 | 0
13 |  | MEDIUM | Maharashtra, Rajasthan | Rajasthan | EPCC- 17 Package for Raw Water Pipeline from Nachna to Bagundi â€“ Rajasthan and associated facilities |  |  |  |  | 350 |  | 2019-10-14 | 2019-11-04 |  |  |  | Bids Under Preparation |  |  |  |  | 0 | 0 | 0
14 |  | UNIDENTIFIED | Southern Region | Rajasthan | EPCC- 17 Package for Raw Water Pipeline from Nachna to Bagundi â€“ Rajasthan and associated facilities - Part B |  |  |  |  | 425 |  | 2019-10-15 | 2019-11-05 |  |  |  | Bids Under Preparation |  |  |  |  | 0 | 0 | 0
15 |  | MEDIUM | Gujarat, Madhya Pradesh | West Bengal | Design, Construction, Supply, Installation & Commissioning of Raw Water Pump House, Intake Bridge, Raw Water Main, Water Treatment Plant, Electrical Substation for Intake and Water Treatment Plant with all Civil, Mechanical, Electro-Mechanical & Instrumentation components and other allied works, SCADA for entire system including the Operation & Maintenance of all the works for a period of 5 years by drawal of surface water from river Kumari at Mukutmanipur Dam under West Bengal Piped Water Supply Project (Purulia) Contract Package â€“ 1 A |  |  |  |  | 131.25 |  | 2019-10-16 | 2019-11-06 |  |  |  | Bids Submitted |  |  |  |  | 0 | 0 | 0
16 |  | UNIDENTIFIED | Southern Region | Chandigarh | Rehabilitation Upgradation of 5 Noâ€™s Existing Sewage Treatment Plant and Construction of 1 No new STP on Design Build and Operate, One Year DLP Plus 15 Years O&M basis at Chandigarh Under Smart City Mission. |  |  |  |  | 55.577 |  | 2019-10-17 | 2019-11-07 |  |  |  | Bids Under Consideration |  |  |  |  | 0 | 0 | 0
17 |  | HIGH | West Bengal, Jharkhand | Jharkhand | Renovation work of selected projects under JMADA Dhanbad Water supply scheme (2nd Call) |  |  |  |  | 282.77 |  | 2019-10-18 | 2019-11-08 |  |  |  | Bid Won |  |  |  |  | 0 | 0 | 0
| GRAND TOTAL |  |  |  | 0 |  |  | GRAND TOTAL |  | 6403.4358 | [11 empty] | 0 | 0 | 0
LEGEND 1: Type of Project: I- Irrigation, WW- Waste Water, R- Rural Water Supply, U- Urban Water Supply Lead Status: T - Tendering / A - Active / P - Preliminary (On horizon) Lead Rating: C - Critical / S - Strategic / R - Regular / O - Yet to be evaluated CR (Client Rating) - A/B/C / O Scope of work : Type of Contract : Item-rate /Cost Plus /Lump sum /Design & Build
Projects Lost
Target projects
Projects Won
0
Formulas:
Date of Submission = [Pre Bid Meeting Date]+21

## Fin->Budget
Project Budget (Plan vs Actual)
Values
Contract Value | Baseline | 445.5
| Revised | 440.1
Budget | Baseline | 410.4
| Revised | 407.2
EBITA (in Cr.)
| Plan | Actual
Sept'19 | 1.2 | 0.9
Nov'19 | 2 | 1.2
Dec'19 | 3 | 2.2
Bonus Achievement of under construction projects (Value in INR)
| Total contract Value | Bonus Achievement (in X) |  | 0.06
Adityapur | 350 | 3.5 | 6% for 6 months
Byamar | 460 | 0 | -
Parwan | 600 | 36 | 2% for 100 days (3.3 months)

## Fin->Claim
JWIL
a. Value of Billable claim opporunity identifed
Project | No of Claims by JWIL | Value of Claims by JWIL
Byarma | 2 | 9
Parwan | 6 | 21.3
Adityapur | 9 | 23.24
b. % claim realized by JWIL
Project | Total Contract Value | % Claims Realized by JWIL | Value of claims paid to subcontractor
Parwan | 600 | 12 | 0
Adityapur | 350 | 3.5 | 0.7
Byarma | 460 | 4.14 | 0.92
% of claim paid to sub contractors
Project | Total Contract Value | Value of claims paid to subcontractor | % of claim paid to sub contractors
Parwan | 600 | 0 | 0
Adityapur | 350 | 0.7 | 0.2
Byarma | 460 | 0.92 | 0.2
Project | Value of Claims by JWIL | % Claims Realized by JWIL
Byarma | 9 | 12
Parwan | 21.3 | 3.5
Adityapur | 23.24 | 4.14

## Fin->Cashflow
AOP |  | Plan | Actual
| Month 1 | 11 | 3
| Month 2 | 15 | 5
| Month 3 | 20 | 15

## Financials
#15 BUDGET
|  | Baseline | Consumed/ Billed
Contract Value | Baseline | 445.5 | 96.1028
| Revised | 440.31 | 96.1028
Budget | Baseline | 410.44 | 91.3065
| Revised | 407.12 | 91.3065
#19 EBITA (in Crs.)
| 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01
EBITA (in Crs.) | -1.52 | -1.51 | 1.21 | -0.96
#Revenue From Inhouse Operations (in Crs.)
| Total Revenue | Revenue from In-house Operations
Amount | 200 | 20

## IA- Observations
Quarter | Report | Low Obs | Med Obs | High Obs | Repeat Observations
Q3 | Report 1 | 1 | 2 | 3 | 3
Q3 | Report 2 | 3 | 2 | 1 | 2
Q3 | Report 3 | 2 | 4 | 6 | 4
Q2 | Report 4 | 1 | 3 | 5 | 1
Q3 | Report 5 | 5 | 3 | 1 | 6
Q4 | Report 6 | 3 | 5 | 1 | 3
Q4 | Report 7 | 1 | 4 | 7 | 2
Q1 | Report 8 | 6 | 3 | 0 | 4
Q1 | Report 9 | 8 | 2 | 3 | 1
Q3 | Report 10 | 2 | 4 | 5 | 3
Q4 | Report 11 | 4 | 6 | 2 | 4
Q3 | Report 1 | 1 | 2 | 3 | 3
Q3 | Report 2 | 3 | 2 | 1 | 2
Q3 | Report 3 | 2 | 4 | 6 | 4
Q2 | Report 4 | 1 | 3 | 5 | 1
Q3 | Report 5 | 5 | 3 | 1 | 6
Q4 | Report 6 | 3 | 5 | 1 | 3
Q4 | Report 7 | 1 | 4 | 7 | 2
Q1 | Report 8 | 6 | 3 | 0 | 4
Q1 | Report 9 | 8 | 2 | 3 | 1
Q3 | Report 10 | 2 | 4 | 5 | 3
Q4 | Report 11 | 4 | 6 | 2 | 4

## IA Audit
Quarter | (All)
Row Labels | Sum of Low Obs | Sum of Med Obs | Sum of High Obs | Sum of Repeat Observations
Report 1 | 2 | 4 | 6 | 6
Report 10 | 4 | 8 | 10 | 6
Report 11 | 8 | 12 | 4 | 8
Report 2 | 6 | 4 | 2 | 4
Report 3 | 4 | 8 | 12 | 8
Report 4 | 2 | 6 | 10 | 2
Report 5 | 10 | 6 | 2 | 12
Report 6 | 6 | 10 | 2 | 6
Report 7 | 2 | 8 | 14 | 4
Report 8 | 12 | 6 | 0 | 8
Report 9 | 16 | 4 | 6 | 2
Grand Total | 72 | 76 | 68 | 66

## IA- Action taken
Quarter | Report | Open observations | Closed Observations | Ageing days
Q3 | Report 1 | 1 | 2 | 1
Q3 | Report 2 | 3 | 2 | 2
Q3 | Report 3 | 2 | 4 | 3
Q2 | Report 4 | 1 | 3 | 4
Q3 | Report 5 | 5 | 3 | 5
Q4 | Report 6 | 3 | 5 | 6
Q4 | Report 7 | 1 | 4 | 1
Q1 | Report 8 | 6 | 3 | 2
Q1 | Report 9 | 8 | 2 | 3
Q3 | Report 10 | 2 | 4 | 4
Q4 | Report 11 | 4 | 6 | 5
Q3 | Report 1 | 1 | 2 | 1
Q3 | Report 2 | 3 | 2 | 2
Q3 | Report 3 | 2 | 4 | 3
Q2 | Report 4 | 1 | 3 | 4
Q3 | Report 5 | 5 | 3 | 5
Q4 | Report 6 | 3 | 5 | 6
Q4 | Report 7 | 1 | 4 | 1
Q1 | Report 8 | 6 | 3 | 2
Q1 | Report 9 | 8 | 2 | 3
Q3 | Report 10 | 2 | 4 | 4
Q4 | Report 11 | 4 | 6 | 5

## IA- Action Take Agening
Quarter | (All)
Ageing days | (All)
Row Labels | Sum of Open observations | Sum of Closed Observations
Report 1 | 2 | 4
Report 10 | 4 | 8
Report 11 | 8 | 12
Report 2 | 6 | 4
Report 3 | 4 | 8
Report 4 | 2 | 6
Report 5 | 10 | 6
Report 6 | 6 | 10
Report 7 | 2 | 8
Report 8 | 12 | 6
Report 9 | 16 | 4
Grand Total | 72 | 76

## Process CP
Row Labels | Sum of No of control points | Sum of Control points adhered | Sum of Total Templates | Sum of Templates adhered
Billing to collection | 8 | 1 | 7 | 5
Contract Award to Closure | 5 | 6 | 4 | 3
Contract To Plan | 5 | 2 | 10 | 7
Employee onboarding to exit | 25 | 3 | 7 | 5
Execution to O&M | 10 | 7 | 6 | 4
F&A | 4 | 4 | 6 | 2
Internal Audit | 3 | 2 | 8 | 6
Plan To Execution | 30 | 22 | 7 | 5
Source to pay - V | 30 | 25 | 7 | 5
Source to pay -SC | 28 | 22 | 5 | 3
Tender to Contract | 15 | 1 | 18 | 10
Grand Total | 163 | 95 | 85 | 55

## Control testing status
Workflows | No of control points | Control points adhered | Total Templates | Templates adhered
Tender to Contract | 15 | 1 | 18 | 10
Contract To Plan | 5 | 2 | 10 | 7
Plan To Execution | 30 | 22 | 7 | 5
Execution to O&M | 10 | 7 | 6 | 4
Source to pay - V | 30 | 25 | 7 | 5
Source to pay -SC | 28 | 22 | 5 | 3
Contract Award to Closure | 12 | 10 | 5 | 4
Billing to collection | 8 | 1 | 7 | 5
Internal Audit | 3 | 2 | 8 | 6
Employee onboarding to exit | 25 | 3 | 7 | 5
F&A | 4 | 4 | 6 | 2

## STP
S.No | Venador Name | Vendor Ranking | Quarter | Feedback Score
1 | Vendor 1 | 3 | Q1 | 8%
2 | Vendor 2 | 4 | Q2 | 7
3 | Vendor 3 | 2 | Q3 | 9
4 | Vendor 4 | 6 | Q1 | 6
5 | Vendor 5 | 4 | Q4 | 9
6 | Vendor 6 | 8 | Q2 | 8
7 | Vendor 7 | 1 | Q3 | 8
8 | Vendor 8 | 9 | Q2 | 7
9 | Vendor 9 | 10 | Q4 | 6
10 | Vendor 10 | 7 | Q3 | 5
Average Ratinng from Top 5 Vendor
Quarter 1 | 7
Quarter 2 | 6.5
Quarter 3 | 8
Quarter 4 | 7

## HR
Technical
Behavioral
Succession
Vendor Development
# | Name | Designation | Project | Employee Score | Employee Interaction Session (Department Name) | Suggestions By Employee | Type of Training | Requirement Identification date | Employee Onboarding Date | TAT for Hiring | Within TAT (<45 Days)
1 | Name 1 | D1 | Project 1 | 45 | CEO | 2 | Behavioral | 2019-03-10 | 2019-05-09 | 60 | N | Y
2 | Name 2 | D2 | Project 2 | 85 | CFO | 3 | Technical | 2019-02-08 | 2019-04-04 | 55 | N
3 | Name 3 | D3 | Project 3 | 90 | BD | 1 | Vendor Development | 2019-03-11 | 2019-05-10 | 60 | N
4 | Name 4 | D4 | Project 4 | 60 | Contracts | 4 | Succession | 2019-02-09 | 2019-04-05 | 55 | N
5 | Name 5 | D5 | Project 5 | 76 | Commercial | 2 | Behavioral | 2019-03-12 | 2019-05-11 | 60 | N
6 | Name 6 | D1 | Project 6 | 87 | Planning | 4 | Technical | 2019-02-10 | 2019-04-06 | 55 | N
7 | Name 7 | D2 | Project 7 | 92 | Billing | 1 | Vendor Development | 2019-03-13 | 2019-04-12 | 30 | Y
8 | Name 8 | D3 | Project 8 | 73 | Legal | 4 | Succession | 2019-02-11 | 2019-04-07 | 55 | N
9 | Name 9 | D4 | Project 9 | 67 | HR | 1 | Behavioral | 2019-03-14 | 2019-05-13 | 60 | N
10 | Name 10 | D5 | Project 10 | 75 | Contracts | 4 | Technical | 2019-02-12 | 2019-04-08 | 55 | N
11 | Name 11 | D1 | Project 11 | 79 | Commercial | 2 | Vendor Development | 2019-03-15 | 2019-04-24 | 40 | Y
12 | Name 12 | D2 | Project 12 | 59 | Planning | 1 | Succession | 2019-02-13 | 2019-04-09 | 55 | N
13 | Name 13 | D3 | Project 3 | 69 | Billing | 4 | Behavioral | 2019-03-16 | 2019-04-15 | 30 | Y
14 | Name 14 | D4 | Project 4 | 98 | Legal | 1 | Technical | 2019-02-14 | 2019-04-10 | 55 | N
15 | Name 15 | D5 | Project 5 | 76 | HR | 4 | Vendor Development | 2019-03-11 | 2019-05-10 | 60 | N
16 | Name 16 | D1 | Project 6 | 78 | CEO | 2 | Succession | 2019-02-09 | 2019-04-05 | 55 | N
17 | Name 17 | D2 | Project 7 | 98 | CFO | 2 | Behavioral | 2019-03-12 | 2019-05-11 | 60 | N
18 | Name 18 | D3 | Project 8 | 65 | BD | 3 | Technical | 2019-02-10 | 2019-03-12 | 30 | Y
19 | Name 19 | D4 | Project 9 | 78 | Contracts | 5 | Vendor Development | 2019-03-13 | 2019-05-12 | 60 | N
20 | Name 20 | D5 | Project 10 | 45 | Commercial | 4 | Succession | 2019-02-11 | 2019-04-07 | 55 | N
21 | Name 21 | D1 | Project 11 | 85 | Planning | 2 | Behavioral | 2019-03-14 | 2019-04-13 | 30 | Y
22 | Name 22 | D2 | Project 12 | 90 | Billing | 4 | Technical | 2019-02-12 | 2019-04-08 | 55 | N
23 | Name 23 | D3 | Project 3 | 60 | Legal | 1 | Vendor Development | 2019-03-15 | 2019-04-14 | 30 | Y
24 | Name 24 | D4 | Project 4 | 76 | HR | 4 | Succession | 2019-02-13 | 2019-04-09 | 55 | N
25 | Name 25 | D5 | Project 3 | 87 | Contracts | 1 | Behavioral | 2019-03-16 | 2019-04-25 | 40 | Y
26 | Name 26 | D1 | Project 4 | 92 | Commercial | 4 | Technical | 2019-02-14 | 2019-04-10 | 55 | N
27 | Name 27 | D2 | Project 5 | 73 | Planning | 2 | Vendor Development | 2019-03-17 | 2019-05-16 | 60 | N
28 | Name 28 | D3 | Project 6 | 67 | Billing | 2 | Succession | 2019-02-15 | 2019-04-11 | 55 | N
29 | Name 29 | D4 | Project 7 | 75 | Legal | 3 | Behavioral | 2019-03-12 | 2019-04-21 | 40 | Y
30 | Name 30 | D5 | Project 8 | 79 | HR | 5 | Technical | 2019-02-10 | 2019-04-06 | 55 | N
31 | Name 31 | D1 | Project 9 | 59 | CEO | 4 | Vendor Development | 2019-03-13 | 2019-05-12 | 60 | N
32 | Name 32 | D2 | Project 10 | 69 | CFO | 2 | Succession | 2019-02-11 | 2019-04-07 | 55 | N
33 | Name 33 | D3 | Project 11 | 98 | BD | 4 | Behavioral | 2019-03-14 | 2019-05-13 | 60 | N
34 | Name 34 | D4 | Project 12 | 76 | Contracts | 1 | Technical | 2019-02-12 | 2019-04-08 | 55 | N
35 | Name 35 | D5 | Project 3 | 78 | Commercial | 4 | Vendor Development | 2019-03-15 | 2019-04-24 | 40 | Y
36 | Name 36 | D1 | Project 4 | 98 | Planning | 1 | Succession | 2019-02-13 | 2019-04-09 | 55 | N
37 | Name 37 | D2 | Project 5 | 65 | Billing | 4 | Behavioral | 2019-03-16 | 2019-05-15 | 60 | N
38 | Name 38 | D3 | Project 6 | 78 | Legal | 2 | Technical | 2019-02-14 | 2019-03-26 | 40 | Y
39 | Name 39 | D4 | Project 7 | 87 | HR | 2 | Vendor Development | 2019-03-17 | 2019-05-16 | 60 | N
40 | Name 40 | D5 | Project 8 | 79 | Contracts | 3 | Succession | 2019-02-15 | 2019-04-11 | 55 | N
41 | Name 41 | D1 | Project 9 | 88 | Commercial | 5 | Behavioral | 2019-03-18 | 2019-04-27 | 40 | Y
42 | Name 42 | D2 | Project 10 | 70 | Planning | 4 | Technical | 2019-02-16 | 2019-04-12 | 55 | N
43 | Name 43 | D3 | Project 11 | 80 | Billing | 2 | Vendor Development | 2019-03-13 | 2019-04-22 | 40 | Y
|  |  |  | 76.8372 |  | 120 |  |  |  | 51.0465 | 12
27.91%
Formulas:
Employee Onboarding Date = [Requirement Identification date]+60
Requirement Identification date = [Requirement Identification date, row above]-30

## HR Working
Row Labels | Average of Employee Score
Project 1 | 45
Project 10 | 64.75
Project 11 | 85.5
Project 12 | 75
Project 2 | 85
Project 3 | 76.8
Project 4 | 84.8
Project 5 | 72.5
Project 6 | 77.5
Project 7 | 88
Project 8 | 74
Project 9 | 73
Grand Total | 76.8372
| High Performers | Voluntary Attrition | Misc.
Month 1 | 4.3 | 2.4 | 2
Month 2 | 2.5 | 4.4 | 2
| Month 1 | Month 2
High Performers | 4.3 | 2.5
Voluntary Attrition | 2.4 | 4.4
Misc. | 2 | 2

## Stakeholder->Litigation
No. of Litigations filed by Client, Partner, Vendor & FI | [5 empty] | Project Name | Month | Litigation Claimed By
| Month 1 |  | Projects |  |  | Adityapur | Jan | Client
| Month 1 | Month 2 | Adityapur | Parwan | Baymar | Parwan | Feb | Partner
Client | 1 | 3 | 5 | 6 |  | Baymar | Mar | Vendor
Partner | 2 | 4 | 5 | 6 |  | Adityapur | May | FI
Vendor | 3 | 4 | 5 | 6 |  | Parwan | June | Client
FI | [5 empty] | Baymar | July | Partner
[6 empty] | Adityapur | Jan | Vendor
[6 empty] | Parwan | Feb | Partner
[6 empty] | Baymar | April | Vendor
[6 empty] | Adityapur | June | Partner
[6 empty] | Parwan | July | Vendor
[6 empty] | Baymar | Jan | FI

## Litigation Backup
Row Labels | Month | Litigation Claimed By | Count of Litigation Claimed By
Adityapur | Jan | Client | 1
|  | Vendor | 1
| Jan Total |  | 2
| May | FI | 1
| May Total |  | 1
| June | Partner | 1
| June Total |  | 1
Adityapur Total |  |  | 4
Baymar | April | Vendor | 1
| April Total |  | 1
| Jan | FI | 1
| Jan Total |  | 1
| Mar | Vendor | 1
| Mar Total |  | 1
| July | Partner | 1
| July Total |  | 1
Baymar Total |  |  | 4
Parwan | Feb | Partner | 2
| Feb Total |  | 2
| June | Client | 1
| June Total |  | 1
| July | Vendor | 1
| July Total |  | 1
Parwan Total |  |  | 4
Grand Total |  |  | 12

## Leads Summary-Region Wise
ORDER BOOKING
S.No. | Region | Achieved Previous Year | Target Current Year | Acieved Current Year | Bids Submitted | Bids Won | Bids Lost | Bids Under Consideration | Shortfall | Wins with High Lead Score
1 | Delhi + Bihar + International | 1700 | 200 | 0 | 1000 | 0 | 0 | 200 | 0 | 1001.2369
2 | Maharashtra, Rajasthan |  | 400 | 0 | 500 | 0 | 0 | 200 | 200
3 | Uttar Pradesh |  | 200 | 0 | 0 | 0 | 0 | 0 | 200
4 | Southern Region |  | 300 | 0 | 250 | 0 | 250 | 0 | 300
5 | HP, Chandigarh, Haryana, Punjab |  | 200 | 0 | 550 | 0 | 0 | 200 | 0
6 | Gujarat, Madhya Pradesh |  | 500 | 500 | 700 | 500 | 0 | 0 | 0
7 | West Bengal, Jharkhand |  | 200 | 0 | 300 | 0 | 0 | 0 | 200
|  | 1700 | 2000 | 500 | 3300 | 500 | 250 | 600 | 900 | 1001.2369